## FY24-25 Grants
FY24-25 GRANT TRACKER
DEPARTMENT | PROJECT | GRANT | CITY MATCH | APPLICATION SUBMITTED | DESIGN | CONSTRUCTION / IMPLEMENTATION | PROJECT STATUS | NOTES
Airport | Airport Master Plan - FAA & ADOT | 510000 | 0 | TRUE | TRUE | FALSE | 66.67% | PO issued 9/1/23-In progress
Airport | Airport Utilities Extension - DCIP | 6930000 | 704905 | TRUE | TRUE | FALSE | 66.67% | Grant not Awarded
Airport | Reconstruction project near self-serve fuel-ADOT | 150000 | 0 | TRUE | FALSE | FALSE | 33.33% | Sharon has proposal from C&S
Airport | Runway Rehab & New Taxiway Connector | 159918 | 0 | FALSE | FALSE | FALSE | 0% | Sharon is writing a memo
CDBG | Montebello Fire Safety Improvements - CDBG HUD | 162575 | 0 | TRUE | TRUE | FALSE | 66.67% | Plans & specs approved-water design report pending approval-waiting on Liberty Water
Museum | Renovation - Tohono O'odham | 65000 | 0 | TRUE | TRUE | TRUE | 100% | Expected completion in June
Parks | Soldier Creek Park (Carryover) | 227172 | 0 | TRUE | TRUE | TRUE | 100% | Completed
Parks | AZ Diamondbacks Grant | 1000000 | 0 | TRUE | FALSE | FALSE | 33.33% | Application submitted- Not Awarded
Parks | Garden Canyon Linear Park/St Andrews Phase II - AZ State Parks | 150000 | 8550 | TRUE | TRUE | TRUE | 100% | Construction substantially complete
Parks | Garden Canyon Linear Park Bathrooms | 120000 | 29700 | TRUE | FALSE | FALSE | 33.33% | Pending resolution
Parks | Archery | 17500 | 17500 | TRUE | FALSE | FALSE | 33.33% | SOW being developed
Parks | Tacoma-sewer/line restrooms | 1000000 | 500000 | FALSE | TRUE | FALSE | 33.33% | In design-pending ADOT permit for potholing and SOW for environmental needed for grant application
Police | VHF Radio System - ADEMA | 350000 | 0 | TRUE | TRUE | TRUE | 100% | Motorola PO completed
Police | Grappler - ADEMA | 70000 | 0 | TRUE | TRUE | TRUE | 100% | Grant expended
Police | License Plate Reader | 300000 | 0 | TRUE | FALSE | FALSE | 33.33% | Awaiting award
Streets | North Garden Construction | 4500000 | 0 | TRUE | FALSE | FALSE | 33.33% | Grant not Awarded-Working on Bid Package to send to Procurement
Streets | State Route Connecter SUP - FTA | 6882943 | 0 | TRUE | FALSE | FALSE | 33.33% | Reapply next year for SR90 Coronaod to Campus
Streets | West End/BST Improvements - RAISE | 20258827 | 0 | TRUE | FALSE | FALSE | 33.33% | RAISE grant submitted on Feb 28-Not Awarded
Streets | City Arterials Pavement Replacement & Overlay | 35766735 | 0 | FALSE | FALSE | FALSE | 0% | Focus on BST - MPDG not applied, congressional appropriations pending
Streets | BST Reconstruction Phase I - Congressional Appropriations | 3792926 | 229265 | TRUE | FALSE | FALSE | 33.33% | Appropriations awarded-ADOT Project Initiation due August 30
Streets | BST Reconstruction Phase II - Appropriations | 7000000 | 0 | TRUE | FALSE | FALSE | 33.33% | Awaiting federal budget passage
Streets | Theater Drive - MPO | 1800000 | 0 | TRUE | TRUE | FALSE | 66.67% | In design - 50%
Streets | HURF Exchange/STBGP | 405000 | 0 | TRUE | TRUE | FALSE | 66.67% | Funds towards MLK Reconstruction-ADOT IGA finalized, design @ 95%
Sewer | Riverstone Phase II | 925000 | 0 | TRUE | FALSE | FALSE | 33.33% | Awaiting completion of Phase 2A
Sewer | Riverstone Phase II - America the Beautiful Grant | 1050000 | 0 | TRUE | FALSE | FALSE | 33.33% | Grant application submitted in July
Transit | Sidewalks (5th, Bel Aire, Judd, Tyalor, SUP Lighting, Bartow, Fab) - FTA | 2000000 | 500000 | TRUE | TRUE | FALSE | 66.67% | Design received-30% plans for review
Transit | Ped Walkway Connection (Carmichael,Timothy, Bartow, Marianne, Kayten & Taylor, Solar Lights at Montebello) - FTA | 1023038 | 255759 | TRUE | TRUE | FALSE | 66.67% | Bid Awarded to KE&G-Start Sep 1st
Transit | Solar Lights @ Montebello |  | 0 | TRUE | TRUE | FALSE | 66.67% | Work to begin in October 2024
Transit | BST Pathway Conectivity - FTA | 790053 | 197512 | TRUE | TRUE | FALSE | 66.67% | In design - 50%
Transit | SR92 Pathway Connectivity - FTA | 546058 | 136515 | TRUE | TRUE | FALSE | 66.67% | Plans finalized-sending to Procurement to bid
Transit | Multi-Use Paths (Oakmont/El Camino, Bypass-7th to Coronado, Bypass-Coronado to Campus) - FTA | 2000000 | 500000 | TRUE | FALSE | FALSE | 33.33% | Not Awarded - Requires NEPA if submitted again
Transit | Two small buses | 200000 | 50000 | TRUE | FALSE | FALSE | 33.33% | Specs being developed
Transit | Transit Master Plan - FTA | 160000 | 40000 | TRUE | FALSE | FALSE | 33.33% | Specs being developed
|  | 100312745 | 3169706